PROJECT BRIEF

Title:				Dedicated Music Experience

Intended opening date:		2 months from today

Overview:

It is intended to use the 2 Hazel Rooms (1 and 2) as a dedicated music experience area of the centre. We intend to open exactly 8 weeks from today.

The  activities below are planned to take place:

- Music Theatre (room 1) – fully equipped with sound systems, a stage or floor area for musicians to perform and a seating area for audience.  This room will double as a Relax and Unwind area and therefore the seating area also needs to include soft seating and small tables. Soft coloured lights are required.

- Music Therapy (room 2) – equipped with a variety of instruments including drums.  This room needs to have some sound proofing work carried out.  It will also need a full recording system to be set up.

- Music workshops – large equipment such as drums can be used from the Music therapy room.  In addition there should be enough Wind and Strings instruments for 6 people.  There will be presentation equipment installed.

We are currently waiting for the sound system and floor to be installed in the Music Theatre and this will be complete in 5 days time.  Once this is complete we will need to purchase the seating and lighting.  These have already been chosen and Sue Rutlidge has a list with all the details on but you will need to send the order in.    This room will be available only on Monday and Wednesday for installations.

All musical equipment has already been selected and Sue should have purchased it, please check with Sue the date she is expecting delivery and put this on the calendar and arrange with Brian to be available for unpacking and storing the items on the day they will be delivered.

Sound Proofing has been provisionally booked (for two weeks from today) and you will need to confirm this by email with the engineers that Mike Prescott is organising.     The recording system (Room 2) can go ahead and be set up – Brian and James will do the set up please add this to the project management and diaries and allow them 2 days.

To advertise the open day we will need the marketing team to put together a marketing plan.  This should be ready this time next week and you should have a copy of that plan.

Any documents or files that you prepare must be saved in the Music Experience Folder.  All file names MUST start with the letters ME  ie MEreport1.doc

Thanks Mr Reiden